TITLE 35:  ENVIRONMENTAL PROTECTION

SUBTITLE C:  WATER POLLUTION

CHAPTER II:  ENVIRONMENTAL PROTECTION AGENCY

PART 362

PROCEDURES FOR ADMINISTRATION OF THE CONSTRUCTION

MANAGEMENT ASSISTANCE PROGRAM FOR GRANTS UNDER THE

CLEAN WATER ACT

SUBPART A:  GENERAL

Section

362.101   Administration

362.102   Definitions

362.103   Project Priority List

362.104   Grant Assistance Availability

362.105   Initiation of Work

SUBPART B:  PROCEDURES FOR ISSUANCE OF

STEP 2 + 3 OR STEP 3 GRANTS

Section

362.201   Review and Approval of Step 2 + 3 Grants

362.202   Review and Approval of Step 3 Grants

SUBPART C:  PROCEDURES FOLLOWING THE ADVERTISEMENT

FOR BUILDING BIDS

Section

362.301   Bid Proposal and Proposed and Executed  Contract

362.302   Addenda and Change Orders

362.303   Operation and Maintenance Manuals

362.304   Requests for Payment

AUTHORITY:  Implementing and authorized by Title II federal  Clean Water

Act, (33 U.S.C. 1285(g)), and Section 4 of the  Environmental Protection

Act (Ill. Rev. Stat. 1983, ch. 111  1/2, par. 1004).

SOURCE:  Adopted and codified at 8 Ill. Reg. 6156, effective  July 1, 1984.

SUBPART A:  GENERAL

<BSection 362.101  Administration>>

a)  Title II of the federal Clean Water Act (33 U.S.C.  1281 et seq.),

authorizes the issuance of grants for the  construction of sewage

treatment works by municipalities and  other units of local

government.  In addition, Section 205(g),  33 U.S.C. 1285(g)

authorizes the delegation to States of the  responsibility to

manage the construction assistance program  set forth in Title II.

b)  The construction management assistance program is  administered in

Illinois on a joint cooperative basis by the  Illinois

Environmental Protection Agency ("Agency") and the  United States

Environmental Protection Agency ("USEPA") in  accordance with

state and federal laws and regulations, these  procedures,

delegation agreements executed by the Agency and  USEPA, and the

Agency's Annual Water Pollution Control Program  Plan as approved

by the USEPA in accordance with Section 106  of the federal Clean

Water Act (33 U.S.C. 1256).

<BSection 362.102  Definitions>>

Unless specified otherwise all terms shall have the meanings  set forth in

the federal Clean Water Act (33 U.S.C. 1251 et  seq.) and 40 CFR 35.

Federal regulations referenced in this  Part will be applicable as of the

effective date of this Part.

<BSection 362.103  Project Priority List>>

The Agency maintains a list setting forth the priority for  receipt of

federal funding for each project applicant.   Project priorities are

established in accordance with Agency  rules entitled "Procedures and

Requirements for Determining  Construction Grant Priorities for Municipal

Sewage Treatment  Works Needs" (35 Ill. Adm. Code 364).  The Project

Priorities  list may be obtained from the Agency upon request.

<BSection 362.104  Grant Assistance Availability>>

a)  For projects on the Project Priority List, the  following grant

assistance is available, subject to the  availability of funding

under federal appropriation:

1)  Step 1 (facilities planning).  No grant  assistance is

available for Step 1, except for amendments to  existing Step

1 grants.  If a Step 3 or Step 2 + 3 grant is  later offered,

an allowance for facility planning may be  provided by the

USEPA at the prevailing federal share.

2)  Step 2 (design engineering and specifications).   No grant

assistance is available for Step 2, except for  amendments to

existing Step 2 grants.  If a Step 3 grant is  later offered,

an allowance for design engineering and  specifications may

be provided by the USEPA at the prevailing  federal share.

If a Step 2 + 3 grant is offered, Step 2 will  consist of an

allowance for design engineering and  specifications at the

prevailing federal share.

3)  Step 3 (building).  Step 3 grants at the  prevailing federal

share are available in accordance with the  approved Water

Pollution Control Program Plan to grant  applicants with a

Grant Priority Index of 94 or higher as  established under 35

Ill. Adm. Code 364.  Funding for Step 3  for projects

utilizing innovative or alternative wastewater  systems with

a Grant Priority Index of less than 94 is  contingent upon

the availability of funds for alternative and  innovative

projects.  Where no Step 1 and Step 2 grants, or  Step 1

grant and advance of allowance for Step 2, have been

previously awarded, the Step 3 grant will include the federal

share of the allowance for both facilities planning and

design  engineering and specifications.  Where a Step 1 grant

has been  previously awarded, and no Step 2 grant or advance

of  allowance for Step 2 has been previously awarded, the

Step 3  grant will include the federal share of the allowance

for  design engineering and specifications only.  Step 3

grants  will include the federal share of the total estimated

eligible  Step 3 costs.

4)  Step 2 + 3 (design engineering and specifications  and

building).  Step 2 + 3 grants at the prevailing federal

share are available in accordance with the approved Water

Pollution Control Program Plan to grant applicants with a

Grant Priority Index of 94 or higher as established under 35

Ill. Adm. Code 364, and which have a population of 25,000 or

less, a total estimated Step 3 building cost of $8 million or

less, and a project that is not phased or segmented.  Step 2

+  3 funding for projects using alternative or innovative

wastewater systems which qualify for a Step 2 + 3 grant, and

with a Grant Priority Index of less than 94, is contingent

upon the availability of funds for alternative and innovative

projects.  Where no Step 1 grant has been previously awarded,

the Step 2 + 3 grant will include the federal share of the

allowance for facilities planning and design.  Where a Step 1

grant has been previously awarded, the Step 2 + 3 grant will

include the federal share of the allowance for design

engineering and specifications only.  The  Step 2 + 3 grant

will include the federal share of the total  estimated

eligible Step 3 costs.

5)  Advance of allowance

A)  Advance of the federal share of an allowance is

available to a community with a population of 25,000 or

less  and which is eligible for the advance under 40 CFR

35, Subpart  I.  The advance shall not exceed the

federal share of the  allowance for such costs received.

B)  Where an advance of allowance has been awarded  to a

grantee that subsequently refuses to accept a Step 2 + 3

or Step 3 grant, the grantee shall repay the advance.

Where a  Step 2 + 3 or Step 3 grant is awarded to a

grant recipient  that has received an advance, the

federal share of the  allowance will be reduced by the

amount of the advance.

b)  The federal share for total eligible Step 3 costs,  the allowance

for both Step 1 and Step 2, the allowance for  Step 2 only, and

the advance of allowance, is as follows:

1)  75 percent for grant assistance awarded before  October 1,

1984.

2)  55 percent for grant assistance awarded after  September 30,

1984, except that grant assistance shall be  available at 75

percent for sequential phases or segments of  an eligible

project under 40 CFR 35, Subpart I where such  project is

described in the facilities plan, and the Step 3  grant for

the initial phase or segment was awarded prior to  October 1,

1984.

3)  85 percent for grant assistance awarded before  October 1,

1984 for projects utilizing innovative or  alternative

wastewater conveyance and treatment systems.   After

September 30, 1984, grant assistance for such projects  is

available at 75 percent, or 85 percent if the project is a

sequential phase or segment of an eligible project under 40

CFR 35, Subpart I.

<BSection 362.105  Initiation of Work>>

Except as provided under 40 CFR 35, Subpart I, the applicant  must not

initiate Step 3 building prior to issuance of a Step  2 + 3 or Step 3 grant

agreement.

SUBPART B:  PROCEDURES FOR ISSUANCE OF

STEP 2 + 3 OR STEP 3 GRANTS

<BSection 362.201  Review and Approval of Step 2 + 3 Grants>>

a)  Each application for a Step 2 + 3 grant shall  include a

facilities plan.  The Agency shall review the  application, the

facilities plan, and other information to  determine if it is

complete and approvable under 40 CFR 35,  Subpart I.

b)  If the facilities plan and supporting application  materials are

complete and approvable, the Agency shall  certify the project to

the USEPA for issuance of a Step 2 + 3  grant in accordance with

the availability of federal funding  if necessary to obligate the

reserve set aside for projects  utilizing innovative or

alternative wastewater conveyance and  treatment systems.

c)  If the facilities plan and supporting application  materials are

not complete and approvable, the Agency shall  issue a letter of

review to the applicant identifying the  deficiencies in the

application which must be corrected prior  to certification of the

Step 2 + 3 grant.  Subject to federal  appropriation, the Agency

will certify a Step 2 + 3 project  where a facility plan is

incomplete if the requirements of 40  CFR 35, Subpart I pertaining

to facility planning exceptions  are met.

d)  Issuance of a Step 2 + 3 grant shall constitute  approval of a

facility plan (except where issued under a  facility planning

exception) and authorization to initiate the  preparation of

design engineering and specifications under the  allowance

provision.

e)  Prior to authorization to advertise for building  bids under Step

3 of the Step 2 + 3 grant, the applicant shall  submit to the

Agency application information required for  issuance of Step 3

grants, together with a user charge system,  and sewer use

ordinance.  The Agency shall authorize the  advertising for

building bids upon a determination that the  submitted information

meets the requirements of 40 CFR 35,  Subpart I.

<BSection 362.202  Review and Approval of Step 3 Grants>>

a)  Each application for a Step 3 grant shall include  the information

required under 40 CFR 35, Subpart I, together  with a sewer use

ordinance and user charge system that meet  the requirements of 40

CFR 35, Subpart I.  The Agency shall  review the application to

determine if it is complete and  approvable.

b)  If the application materials are complete and  approvable the

Agency shall certify the project to the USEPA  for issuance of a

Step 3 grant in accordance with the  availability of federal

funding.

c)  If the application materials are not complete and  approvable, the

Agency shall issue a letter of review to the  applicant,

identifying the deficiencies in the application  which must be

corrected prior to certification of the Step 3  grant.

d)  Subject to federal appropriation, the Agency will  certify a Step

3 project where a facility plan is incomplete  if the requirements

of 40 CFR 35, Subpart I, pertaining to  facility planning

exceptions and segmentation of projects are  met.

e)  Issuance of a Step 3 grant shall constitute approval  of a

facility plan (except where issued under a facility  planning

exception), final design, and authorization to  advertise for

building bids.

SUBPART C:  PROCEDURES FOLLOWING THE ADVERTISEMENT

FOR BUILDING BIDS

<BSection 362.301  Bid Proposal and Proposed and Executed  Contract>>

a)  After advertisement for and receipt of building  bids, the

applicant shall submit to the Agency for review  those documents

necessary to determine compliance with 40 CFR  33 including:  the

bid tabulation, bid analyses, the bid  proposal, and the proposed

contract and any request for  amendment to the Step 3 grant or

Step 3 portion of the Step 2  + 3 grant.  If a grant amendment is

necessary and approvable  in accordance with 40 CFR 35 and this

Part, the Agency shall  issue a certification of the grant

amendment in a transmittal  of the request to the USEPA.  Final

approval by the Agency or the USEPA of the bid proposal and

proposed  contract shall be authorization by the Agency to the

applicant  to award the contract to the lowest responsible,

responsive  bidder.

b)  The executed contract between the grantee and  contractor shall be

submitted to the Agency within 10 days  after execution.

<BSection 362.302  Addenda and Change Orders>>

a)  The grantee shall submit addenda and change orders  to the Agency

for review and approval of any project changes.

b)  The Agency will review all addenda and change orders  to determine

whether or not there is an alteration of the  design, location,

size, capacity, quality or equipment, and to  determine whether or

not a supplemental permit to construct  and/or operate is

necessary.

c)  The Agency will not approve costs of addenda or  change orders

unless such costs are costs for work which is  within the approved

scope of work for which the grant was  offered and unless the

requirements of Section 361.302(d) are  satisfied.

d)

1)  The Agency will approve change orders if the  cumulative

worth of the change orders is less than 3% of the  approved

bid amount.

2)  Notwithstanding Section 362.302(d)(1), the  Agency will

approve change orders whose cumulative worth is  greater than

3% but less than or equal to 5% of the approved  bid amount,

for work which is consistent with the scope of the  grant

project, but could not have been foreseen at the time of

contract approval despite the exercise of due diligence by

the  grantee.

3)  The Agency will not approve change orders whose  cumulative

worth is greater than five percent of the approved  bill

amount.

<BSection 362.303  Operation and Maintenance Manuals>>

The final plan of operation and the operation and maintenance  manual shall

be submitted to the Agency for review and  approval in accordance with

Agency rules entitled  "Requirements for Plans of Operation and Operation

and  Maintenance Manuals."  (35 Ill. Adm. Code 371)

<BSection 362.304  Requests for Payment>>

a)  Requests for partial payment shall be sent directly  to the

Agency.

b)  Requests for final payment shall be sent directly to  the Agency.

The Agency issues a payment in accordance with 40  CFR 30 which

may be up to, but not including, that percentum  of the grant

which is equal to that percent of the contract  price which the

applicant withholds from the contractor,  pending final inspection

and final audit.

1)  The Agency shall conduct an on-site inspection  to determine

whether or not final payment is approvable.  The  inspection

shall be made within 60 days of notification by the

applicant that the building of the project is complete.  The

Agency shall not approve final payment unless verification is

received that:

A)  The project was built in accordance with  permitted

plans and specifications.

B)  For projects to improve at a sewage  treatment plant,

the hydraulic and organic loads to the plant  are less

than plant capacity.

C)  For projects to improve a sewage treatment  plant, the

removal efficiencies are within the design  criteria.

D)  Operation of the facility is under the  direct and

active supervision of operators properly certified  by

the Agency under 35 Ill. Adm. Code 380.

2)  The Agency shall either approve the release of  final payment

or issue a letter to the applicant identifying  any

deficiencies in the building and/or operation of the

completed project.

3)  Final approval of the request for final payment  is issued by

the Agency, following the completion of the final  inspection

by the Agency.